{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["20170811"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"20170811","index":0,"n_rows":6,"n_cols":15,"rows_kept":6,"cut":false,"hidden":false,"merged":[[0,1,0,13],[1,1,1,11],[2,1,2,11],[3,1,3,11],[4,1,4,11],[5,1,5,11],[6,1,6,11],[7,1,7,11],[8,1,8,11],[9,1,9,11],[10,1,10,11],[11,1,11,11],[12,1,12,11],[13,1,13,11],[14,1,14,11],[15,1,15,11],[16,1,16,11],[17,1,17,11]]}
[null,"        工作总结(2017/08/07-2017/08/11)"]
[null,"本周工作内容",{"$nulls":10},"完成进度","计划完成时间","工作人员"]
[null,"1.思敦- 贸易学校项目  修改联调测试中发现的Bug,开发完成贸易学校提供的第三方学生和教职工数据接口，支撑和部署安装应用。   ",{"$nulls":10},1,"8月初","张伟亚，乐云贇"]
[null,"2.思敦- 客户端整合到Web  大体功能基本完成迁移，小部分功能测试没通过，检查是否是设备原因。",{"$nulls":10},0.9,null,"张伟亚"]
[null,"3.思敦- 客户端整合到Web  Server端对外的Http接口迁移到IISWeb端基本完成。初步测试没问题，等待App调用测试。",{"$nulls":10},0.9,null,"张伟亚"]
[null,"4.校友会项目 年会管理， 医疗求助、活动栏目完成，首页修改。后台功能菜单配置完成。",{"$nulls":10},0.7,null,"乐云贇"]